## README
ALLEATO GROUP BILLING TEMPLATE — OWNER BILLING
Your partner from the ground up. · www.alleatogroup.com
WHAT THIS IS
Alleato Group’s standard billing package: Form APP (Application and Certificate for Payment), Form CS (Continuation Sheet) and Form CO (Change Order), built as live formulas so a pay application can be produced, checked and archived without retyping numbers.
Direction of billing: Contractor → Owner.
SHEETS, IN THE ORDER YOU USE THEM
• Setup — project, parties, contract sum, retainage rates, current application period. The only sheet where project data is typed.
• CO Log — every change order. Status must read Approved or Executed to be picked up. The In Prior Application Y/N flag splits the change order summary between prior applications and this one.
• Schedule of Values — the working sheet and the monthly data entry: Scheduled Value (col D), From Previous Application (col E), This Period (col F), Materials Presently Stored (col G), and the prior / released retainage columns. Everything else calculates. Wider than the Continuation Sheet because it carries the retainage detail the platform needs.
• Continuation Sheet — Form CS. The same schedule of values in the standard columns A through I. Every cell is a formula from the Schedule of Values sheet; nothing is typed here. This is the copy you send out.
• Payment Application — Form APP. Reads entirely from the Schedule of Values and CO Log. The only typed cell is Line 7, Less Previous Certificates for Payment.
• Change Order — Form CO. One change order per sheet; duplicate the sheet as needed.
RETAINAGE — 5a / 5b SPLIT
Retainage is tracked per SOV line in three parts, matching how the platform stores it: PRIOR (withheld on earlier applications), THIS PERIOD (calculated from the rate), and RELEASED. Completed work and stored materials are tracked separately, which is what produces Line 5a and Line 5b.
Columns K and O hold the rates and default from Setup — override either on an individual line when that line carries a reduced rate. Columns M and Q calculate this period’s retainage. Columns L and P are typed: carry them forward from the prior application’s held balance.
To release retainage, enter the released amount as a POSITIVE number in column N (work) or column R (materials). Never adjust Line 5 directly — it must always foot to column S, and the sheet warns you if it does not.
All percentages in this workbook are entered out of 100 (type 10 for ten percent), matching the platform’s retainage_pct / work_completed_pct columns. Do not enter 0.10.
MONTHLY ROLLOVER
• Save a copy of the workbook named for the new application number.
• On Setup, bump Application No. and set the new Period From / Period To.
• On the Schedule of Values, copy column H (Total Completed and Stored to Date) and paste-special as VALUES into column E (From Previous Application). Then clear columns F and G.
• Also on the Schedule of Values, paste last month’s held retainage into columns L and P as VALUES (work: L + M − N; materials: P + Q − R), then clear columns N and R.
• On the Payment Application, set Line 7 to the prior application’s Line 6.
• On the CO Log, flip In Prior Application to Y for change orders that were on the last application.
BUILT-IN CHECKS
• Tie-out: the Scheduled Value grand total must equal Line 3, Contract Sum to Date. The cell below the grand total reports OK or the variance.
• Change order summary: net change must tie to Line 2. A warning appears if it does not.
• Retainage: Lines 5a + 5b must foot to column S. A warning appears if they do not.
UPLOADING TO THE ALLEATO PM PLATFORM
The CSV templates shipped alongside this workbook map these sheets to the platform tables. The Schedule of Values columns line up one-for-one with the invoice line item columns, so a completed sheet can be copied straight into the CSV. See CSV-IMPORT-SPEC.md for the column mapping and required load order.
SCOPE OF THESE FORMS
These are Alleato Group forms. They follow the standard construction-industry application-for-payment structure — nine summary lines, the 5a / 5b retainage split, and a continuation sheet with columns A through I — so any owner, lender or subcontractor will read them without friction. Certification language is Alleato’s own. Where a contract specifies submission on a particular third-party form, obtain that form from its publisher and key the figures across from this workbook; use these forms for internal billing preparation, for subcontractor billing, and as the data source for the platform.
ALLEATO GROUP · www.alleatogroup.com
8383 Craig Street, Suite 150, Indianapolis, IN 46250
701 94th Avenue North, Suite 118, St. Petersburg, FL 33702
Your partner from the ground up.

## Setup
PROJECT & CONTRACT SETUP
Fill the white cells once per contract. Every other sheet reads from here.
PROJECT |  | HOW THIS WORKBOOK IS WIRED
Project Name |  | 1. Setup — project, parties, contract sum, retainage rates. Type here only.
Project Number |  | 2. CO Log — log every change order. Feeds the change order summary.
Project Address |  | 3. Schedule of Values — the SOV and the monthly data entry.
Alleato Project ID (projects.id) |  | 4. Payment Application — reads from the SOV + CO Log. Only Line 7 is typed.
OWNER — PAYING PARTY |  | 5. Change Order — one per change. Copy the sheet as needed.
Owner Name |  | MONTHLY ROLLOVER
Owner Address |  | • Copy the workbook, bump Application No., set the new period dates.
CONTRACTOR — PAID PARTY |  | • On the SOV, paste last month’s column H into column E as VALUES, clear F and G.
Contractor Name |  | • On the Payment Application, set Line 7 to last month’s Line 6.
Contractor Address |  | • On CO Log, flip "In Prior Application" to Y for change orders already billed.
Vendor ID (companies.id) |  | RETAINAGE
ARCHITECT / DESIGN PROFESSIONAL |  | • Rates default from here but override per line in SOV columns K and O —
Architect Name |  | that is how you handle a reduced rate or release on a single SOV line.
CONTRACT |  | • Never adjust Line 5 directly; it must always foot to the SOV.
Prime Contract Number |  | ALLEATO GROUP standard billing forms — see the README sheet.
Prime Contract Date
Original Contract Sum | 0
Alleato Contract ID
RETAINAGE — DRIVES LINES 5A / 5B
Retainage % — Completed Work (5a) | 10
Retainage % — Stored Materials (5b) | 10
CURRENT APPLICATION
Application No. | 1
Application Date
Period From
Period To

## CO Log
CHANGE ORDER LOG
One row per change order. Only rows with Status = Approved or Executed are picked up. "In Prior Application" = Y once the change order has appeared on a certified application.
CO NO. | DESCRIPTION | DATE APPROVED | STATUS | ADDITIONS ($) | DEDUCTIONS ($) | SCHEDULE IMPACT (DAYS) | IN PRIOR APPLICATION? (Y/N) | NET ($)
TOTALS — APPROVED / EXECUTED ONLY
Approved in previous applications (In Prior = Y)
Approved this application (In Prior = N)

## Schedule of Values
CONTINUATION SHEET — SCHEDULE OF VALUES
Working schedule of values. Feeds the Continuation Sheet and the Payment Application.
| PROJECT: |  |  |  |  | APPLICATION NO.:
| CONTRACTOR: |  |  |  |  | PERIOD TO:
| PRIME CONTRACT NO.: |  |  |  |  | APP. DATE:
A | B |  | C | D | E | F | G | G/C | H | I | I | I | I | I | I | I | I | I
ITEM NO. | DESCRIPTION OF WORK | BUDGET CODE | SCHEDULED VALUE | WORK COMPLETED FROM PREVIOUS APPLICATION | WORK COMPLETED THIS PERIOD | MATERIALS PRESENTLY STORED | TOTAL COMPLETED AND STORED TO DATE | % | BALANCE TO FINISH | RET % WORK | RET $ WORK PRIOR | RET $ WORK THIS PERIOD | RET $ WORK RELEASED | RET % MATL | RET $ MATL PRIOR | RET $ MATL THIS PERIOD | RET $ MATL RELEASED | TOTAL RETAINAGE HELD
BASE CONTRACT
SUBTOTAL — BASE CONTRACT
APPROVED CHANGE ORDERS
SUBTOTAL — APPROVED CHANGE ORDERS
GRAND TOTAL — CARRIES TO THE PAYMENT APPLICATION
TIE-OUT — Scheduled Value total vs Line 3, Contract Sum to Date:

## Continuation Sheet
CONTINUATION SHEET
Columns A through I only. Every value is a formula from the Schedule of Values sheet — do not type here. This is the transmittal copy.
The Application and Certificate for Payment containing the Contractor’s signed certification is attached. Use Column I on Contracts where variable retainage for line items may apply. |  |  |  |  | APPLICATION NO.:
APPLICATION DATE:
PERIOD TO:
ARCHITECT’S PROJECT NO.:
A | B | C | D | E | F | G |  | H | I
ITEM NO. | DESCRIPTION OF WORK | SCHEDULED VALUE | WORK COMPLETED |  | MATERIALS PRESENTLY STORED (NOT IN D OR E) | TOTAL COMPLETED AND STORED TO DATE (D+E+F) | % (G ÷ C) | BALANCE TO FINISH (C – G) | RETAINAGE (IF VARIABLE RATE)
|  |  | FROM PREVIOUS APPLICATION (D + E) | THIS PERIOD
BASE CONTRACT
SUBTOTAL — BASE CONTRACT
APPROVED CHANGE ORDERS
SUBTOTAL — APPROVED CHANGE ORDERS
GRAND TOTAL
The RETAINAGE column shows total retainage held (completed work + stored materials, net of releases) — column I, "Retainage (if variable rate)". The 5a / 5b breakdown behind it is on the Schedule of Values sheet, columns K through S.

## Payment Application
APPLICATION AND CERTIFICATE FOR PAYMENT
Form APP · Prime Contract · Contractor to Owner
TO OWNER: |  |  | APPLICATION NO.:
APPLICATION DATE:
FROM CONTRACTOR: |  |  | PERIOD FROM:
PERIOD TO:
PROJECT: |  |  | PRIME CONTRACT NO.:
PROJECT NO.: |  |  | PRIME CONTRACT DATE:
VIA ARCHITECT: |  |  | ALLEATO PROJECT ID:
CONTRACTOR’S APPLICATION FOR PAYMENT |  |  |  | CHANGE ORDER SUMMARY
Application is made for payment, as shown below, in connection with the Contract.
[5 empty] | ADDITIONS | DEDUCTIONS
1 | ORIGINAL CONTRACT SUM |  |  | Total changes approved in previous applications by Owner
2 | Net change by Change Orders |  |  | Total approved this application
3 | CONTRACT SUM TO DATE (Line 1 ± Line 2) |  |  | TOTALS
4 | TOTAL COMPLETED AND STORED TO DATE (Continuation Sheet, column G) |  |  | NET CHANGE BY CHANGE ORDERS
5 | RETAINAGE:
5a | of Completed Work (SOV prior + this period − released)
5b | of Stored Material (SOV prior + this period − released)
Total Retainage (Lines 5a + 5b = SOV column S)
6 | TOTAL EARNED LESS RETAINAGE (Line 4 less Line 5 Total) |  |  | PERCENT COMPLETE
7 | LESS PREVIOUS CERTIFICATES FOR PAYMENT (Line 6 from prior Certificate) | 0 |  | RETAINAGE HELD TO DATE
8 | CURRENT PAYMENT DUE
9 | BALANCE TO FINISH, INCLUDING RETAINAGE (Line 3 less Line 6)
CONTRACTOR’S CERTIFICATION
The undersigned contractor certifies that, to the best of its knowledge, information and belief, the Work covered by this Application for Payment has been completed in accordance with the Contract Documents, that all amounts have been paid by the contractor for Work for which previous Certificates for Payment were issued and payments received from the owner, and that the current payment shown herein is now due.
CONTRACTOR (firm): |  |  |  | State of:
By (signature): |  |  |  | County of:
Printed name / title: |  |  |  | Subscribed and sworn to before me this ____ day of ____________, 20____.
Date: |  |  |  | Notary Public:
ARCHITECT’S CERTIFICATE FOR PAYMENT
In accordance with the Contract Documents and based on observations at the site and the data comprising this Application, the architect certifies to the owner that the Work has progressed as indicated, that the quality of the Work is in accordance with the Contract Documents, and that the contractor is entitled to payment of the AMOUNT CERTIFIED.
AMOUNT CERTIFIED
If AMOUNT CERTIFIED differs from CURRENT PAYMENT DUE, attach an explanation and initial every figure changed on this Application and on the Continuation Sheet.
ARCHITECT (firm):
By (signature):
Date:
This Certificate is not negotiable. The AMOUNT CERTIFIED is payable only to the contractor named herein. Issuance, payment and acceptance of payment are without prejudice to any rights of the owner or contractor under the Contract.

## Change Order
CHANGE ORDER
Form CO · Owner ↔ Contractor
PROJECT: |  |  | CHANGE ORDER NO.:
PROJECT NO.: |  |  | DATE:
OWNER: |  |  | PRIME CONTRACT NO.:
CONTRACTOR: |  |  | PRIME CONTRACT DATE:
ARCHITECT: |  |  | ALLEATO PROJECT ID:
THE CONTRACT IS CHANGED AS FOLLOWS
Describe the change in scope, the reason for the change, and reference the authorizing document (RFI, ASI, bulletin, field directive, CCD).
COST BREAKDOWN
DESCRIPTION | BUDGET CODE | QTY | UOM | UNIT COST | AMOUNT
TOTAL THIS CHANGE ORDER
If AMOUNT is entered directly without qty × unit cost, put it in the AMOUNT column and leave QTY / UNIT COST blank.
CONTRACT SUM ADJUSTMENT
The original Contract Sum was
Net change by previously authorized Change Orders |  |  |  | 0
The Contract Sum prior to this Change Order was
The Contract Sum will be increased / (decreased) by this Change Order in the amount of
The new Contract Sum including this Change Order will be
The Contract Time will be increased / (decreased) by |  |  |  |  | calendar days
The date of Substantial Completion as of this Change Order is
NOTE: This Change Order does not include changes in the Contract Sum, Contract Time or Guaranteed Maximum Price that have been authorized by Construction Change Directive until the cost and time have been agreed upon by both parties.
NOT VALID UNTIL SIGNED BY ALL PARTIES BELOW
OWNER |  | ARCHITECT |  | CONTRACTOR
(firm name) |  | (firm name) |  | (firm name)
BY (signature) |  | BY (signature) |  | BY (signature)
(printed name and title) |  | (printed name and title) |  | (printed name and title)
DATE |  | DATE |  | DATE